## Sheet1
Brand | CM | Chipset | MP | Notes
Cisco 1k | FXCN | BRCM 43684 |  | PO in final approval loop (ETA MAR / APR). MP in Q3. 100K-200K volume in 2018, Qty 3-4 units. Added TI 25xx BTLE in IQfact. APT will be needed in Q3 (TBD)
Cisco 2k H | WNC | MRVL 9068 | 2018-08-01 | DVT with M16W and not move to factory yet. Kyle focused on closing 7 unit MW order in Q1 '18
Cisco 3k | FXCN | MRVL 9068 | Q4 2018 | DVT phase
Cisco 2k L | WNC | QCOM 8072 | 2018-10-01 | M8W online at Kunshan Factory for P2 build
Netgear | FXCN | BRCM 43684 | 2018-06-01 | M16Wx 1 PO received and shipment. Target MP in Q3 at Foxconn VN and plan to use M8W. Good shape.
Netgear | DNI | QCOM 8072 |  | NTGR may delay QCOM project and launch BRCM first. SL (SJC) is key, and still pushing KEYS -- unclear why. Need follow up in SJC
Meraki | WNC | QCOM 8072 |  | R&D order in. WNC still using KEYS. Atul visit (3/5) has helped to change opinion of WNC, so we expect change to LP. QCOM FAE has said LP is OK to use
Aruba | WNC | QCOM 8072 |  | R&D orders received. ODM project and WNC working on own SW on top of QSPR. NEed to clarify who WNC to Aruba contacts are (both sides)
Aruba | WNC | BRCM 43684 |  | "4+4 Design" Need info on program from WNC
Aruba | Sercomm | BRCM 43684 |  | "2+4 Design". Smal Volume Build March. Elvin working with Bruce in China (Jack (LP -)) has new role now.
Arris | FXCN | BRCM 43684 |  | Arris TWN firmly on board with LP and recommneding LP to FXCN
Arris | Pegatron | BRCM 43684 |  | Still very early in project. No HW ready yet.
Aerohive | WNC | BRCM 43684 | 2019-05-01 | No R&D order yet. CM using MW. Trial Run May 2018
Extreme Networks | WNC | BRCM 43684 | 2018-06-01 | R&D order in. CM using MW
Belkin | WNC | QCOM 8072 |  | APT x2 solution delivered
UBEE | FXCN | BRCM 43684 |  | XDSL. RD in CN LH and use M8W. Target to have sample run in April in VN, factory is applying M8Wx 5 on PR process.
Huawei | Huawei | QCOM 8074 |  | R&D in Suzhou. MW order in process. KEYS removed from Lab. ATE in Nanjing
Huawei | Huawei | HiSi H123 |  | R&D order in. Chip design still in process. NI and KEYS pushed out.
Huawei | Huawei | MRVL 9068 |  | Compete with QCOM. QCOM is still first priority
TP Link | TP Link | BRCM 43684 |  | R&D order received. MFG schedule not clear, Chip FW still in process
Ruckus | LiteOn | QCOM 8072 | Q3 2018 | Eran Dor meetign on 3/8. Have DUT at LP now. Demo on MW16 to Jeremy on 3/28. VXT is POR for the LiteOn project, but we have a chance to change.
H3C | WNC | QCOM 8072 | 1905-07-11 | WNC Nanjing PO in
NEC | Alpha | QCOM 8072 |  | Alpha R&D order in. Additional 1 M2W order in Q1. Trade-in (EXM) program for MFG