## Sheet1
Brand | CM | Chipset | MP | Notes
Cisco 1k | FXCN | BRCM 43684 |  | PO in final approval loop (ETA MAR / APR). MP in Q3. 100K-200K volume in 2018, Qty 3-4 units. Added TI 25xx BTLE in IQfact. APT will be needed in Q3 (TBD)
Cisco 2k H | WNC | MRVL 9068 | 2019-05-01 | MRVL programs delayed due to chip / feature issues. B0 chip in May
Cisco 3k | FXCN | MRVL 9068 | 2019-05-01 | DVT phase
Cisco 2k L | WNC | QCOM 8072 | 2018-06-01 | EXM at 28k (2 mod) with M8 trade in. Kyle working M8 UG + M8W package deal. Meet Robin 3/30
Netgear | FXCN | BRCM 43684 | 2018-06-01 | M16Wx 1 PO received and shipment. Target MP in Q3 at Foxconn VN and plan to use M8W. Good shape.
Netgear | DNI | QCOM 8072 | Q3 2018 | Demo to SJC team (Jospeph / SL) on 3/28. M16W order coming week of 4/2. Will begin Hawkeye EVAL in SJC (very positive account turn around). Follow up with DNI week of 4/2
Meraki | WNC | QCOM 8072 | 2018-08-01 | Demo to Meraki TWN week of 4/2
Aruba | WNC | QCOM 8072 | Q1 2019 | Meeting on 3/28. Will wait for HK 2.0 -- product not until 2019
Aruba | WNC | BRCM 43684 | Q4 2018 | BRCM program on track and happy with LP.
Aruba | Sercomm | BRCM 43684 | Q4 2018 | IQfact released for DVT
Arris | FXCN | BRCM 43684 |  | April for Program start. Using IQfact. MFG schedule unclear. Arris will consign testers to Naning, PRC
Arris | Pegatron | BRCM 43684 |  | Still very early in project. No HW ready yet.
Aerohive | WNC | BRCM 43684 | 2019-05-01 | No R&D order yet. CM using MW. Trial Run May 2018. Providing IQmeasure Support so WNC can develop own test SW
Extreme Networks | WNC | BRCM 43684 | 2018-08-01 | R&D order in. CM using MW
Belkin (Foxconn) | WNC | QCOM 8072 |  | APT x2 solution delivered based on Belkin DUT
UBEE | FXCN | BRCM 43684 |  | IQfact delivered, but debugging 802.11ac issue (same issue with MFGC -- DUT FW)
Huawei | Huawei | QCOM 8074 | 5/2018 (trial) | R&D in Suzhou. MW order in process. KEYS removed from Lab. ATE in Nanjing. HK 1.1
Huawei | Huawei | HiSi H1152 |  | R&D order in. Chip design still in process. NI and KEYS pushed out.
Huawei | Huawei | HiSi H1103 | 2019-04-01 | STA chip. Only supporting .ac now. Possibly moving from 20% to 40% discount to win most of the share
Huawei | Huawei | MRVL 9068 |  | MRVL B0 chip not until May 2018. Moving to LP as KEYS support is not good
TP Link | TP Link | BRCM 43684 |  | R&D order received. MFG schedule not clear, Chip FW still in process
Ruckus | LiteOn | QCOM 8072 | Q3 2018 | Demo to Shenzhen team on 3/29. Outcome expected on 3/30.
H3C | WNC | QCOM 8072 | 1905-07-11 | WNC Nanjing PO in
D Link | Alpha | BRCM 43684 | Q4 2018 | DVT with M2W. NPI Q3 2018
NEC | Alpha | QCOM 8072 | 2018-08-01 | Alpha R&D order in. Unlcear when volume will ramp beyond Japan Factory (all KEYS). NEC meeting by 3/30 in JPN