## Sheet1
Brand | CM | Chipset | MP | Notes
Cisco 1k | FXCN | BRCM 43684 |  | Budget approved by Michael Lin. PR not yet released (ETA April). Negotiation to start after PR release.
Cisco 2k H | WNC | MRVL 9068 | 2019-05-01 | MRVL programs delayed due to chip / feature issues. B0 chip in May
Cisco 3k | FXCN | MRVL 9068 | 2019-05-01 | DVT phase
Cisco 2k L | WNC | QCOM 8072 | 2018-06-01 | EXM at 28k (2 mod) with M8 trade in. Kyle working M8 UG + M8W package deal. Ongoing business discussions -- workign to meet BU head Larry
Netgear | FXCN | BRCM 43684 | 2018-06-01 | IQfact BRCM_43684_4.0.0.16 Released
Netgear | DNI | QCOM 8072 | Q3 2018 | Order for M16W received from SJC team. Arun to support week of 4/9. Jason to take over on 4/16. Kyle to have meeting with Tony and ACE Frank (week of 4/9)
Meraki | WNC | QCOM 8072 | 2018-08-01 | Meraki demo to WNC on 4/3
Aruba | WNC | QCOM 8072 | Q1 2019 | Will wait for HK 2.0 -- product not until 2019
Aruba | WNC | BRCM 43684 | Q4 2018 | BRCM program on track and happy with LP.
Aruba | Sercomm | BRCM 43684 | Q4 2018 | IQfact v4.0.0.16 released
Arris | FXCN | BRCM 43684 |  | April for Program start. Using IQfact. MFG schedule unclear. Arris will consign testers to Naning, PRC
Arris | Pegatron | BRCM 43684 |  | Still very early in project. No HW ready yet.
Aerohive | WNC | BRCM 43684 | 2019-05-01 | Potential R&D order Q3 18. CM using MW. Trial Run May 2018. Providing IQmeasure Support so WNC can develop own test SW
Extreme Networks | WNC | BRCM 43684 | 2018-08-01 | R&D order in. CM using MW
Belkin (Foxconn) | WNC | QCOM 8072 |  | APT x2 solution delivered based on Belkin DUT
UBEE | FXCN | BRCM 43684 |  | 5 unit PR in process by FXCN Vietnam
Huawei | Huawei Suzhou | QCOM 8074 | 5/2018 (trial) | Price Framework agreement closed on 3/31. 2 unit order expeteced soon (M8W)
Huawei | Huawei | HiSi H1152 / 1103 |  | April 12 meeting planned with Coach (Tian Jun). VXT in lab, but not in use (was purchased earlier), signifies some risk as higher level MGMT may be wanting 2 vendors
Huawei | Huawei | MRVL 9068 |  | MRVL B0 chip not until May 2018. Moving to LP as KEYS support is not good
TP Link | TP Link | BRCM 43684 |  | Magic Lin now covering
Ruckus | LiteOn | QCOM 8072 | Q3 2018 | Successful Demo 3/29. Want to engage on multi-DUT APT. M8W order expected.
H3C | WNC | QCOM 8072 | 1905-07-11 | WNC Nanjing PO in
D Link | Alpha | BRCM 43684 | Q4 2018 | DVT with M2W. NPI Q3 2018
NEC | Alpha | QCOM 8072 | 2018-08-01 | Meeting with NEC factoy in JPN. Impressed by 20% speed improvement on QSPR. Working to get next product business (first product is 2 VXT rentals only)
Calix (Santa Rosa) |  | QCOM 8072 |  | Dan H. to dig into
Star Net (Michigan) |  | QCOM 8072 |  | Dan H. to dig into
VVDN |  | QCOM 8072 |  | PMS to contact