## Sheet1
| Brand | CM | Chipset | MP | Notes
1 | Cisco 1k | FXCN | BRCM 43684 | Q3 2018 | 2 PO received from Foxconn
2 | Cisco 2k H | WNC | MRVL 9068 | 2019-05-01 | MRVL programs delayed due to chip / feature issues. B0 chip in May.
3 | Cisco 3k | FXCN | MRVL 9068 | 2019-05-01 | DVT phase
4 | Cisco 2k L1 | FXCN | BRCM 43694 | Q4 2018 | Initial samples to be built June. "Vancouver". MP will be 4 to 5 sets
5 | Cisco 2k L | WNC | QCOM 8072 | 2018-06-01 | Commecial porposal in. Factory visit week of 5/14
6 | Cisco 1k L | FXCN | BRCM 2x2 |  | New project with new BRCM chip (Aug 2018)
7 | Netgear | FXCN | BRCM 43684 | 2018-09-01 | Verifying latest board with B0 chip
8 | Netgear | DNI | QCOM 8072 | Q3 2018 | IQxel-MW + Hawkeye set up and running at NTGR TWN. After data collected, follow up with Tony at DNI
9 | Netgear | Pegatron | Lantiq ???? |  | Chris is in contact with Lantiq team. Meeting postponed to 5/8. Keep following up Sercomm, Pegatron and TP-link information
10 | Meraki | WNC | QCOM 8072 | Q3 2018
11 | ASUS | Arcadyan | BRCM 43684 | Q4 2018 | KEYS loaner to ASUS. Connected with Asus to check the project status. Very early stage and no much progress.
12 | Aruba | WNC | QCOM 8072 | Q1 2019 | Will wait for HK 2.0 -- product not until 2019
13 | Aruba | WNC | BRCM 43684 | Q4 2018 | BRCM program on track and happy with LP.
14 | Aruba | Sercomm | BRCM 43684 | Q4 2018 | IQfact v4.0.0.16 released. May 2018 200 piece run with IQfact + LPT
15 | Arris | FXCN | BRCM 43684 |  | April for Program start. Using IQfact. MFG schedule unclear. Arris will consign testers to Naning, PRC
16 | Arris | Pegatron | BRCM 43684
17 | Arris | Pegatron | QCOM 8074 |  | SU data rates working. Waiting on HK 1.2 driver (end of June ETA)
18 | Aerohive | WNC | BRCM 43684 | 2019-05-01 | Chih Wei supporting sample run
19 | Extreme Networks | WNC | BRCM 43684 | Q1 2019 | R&D order in. CM using MW
20 | Belkin (Foxconn) | WNC | QCOM 8072 | Q3 2018 | ENG run in August (2 DUT APT)
21 | Fortinet (43XF) | USI | BRCM 43684 | Q4 2018 | (2019 FCST 80k units) 1 M16W lab purchase planned. End Q2 for sample run
22 | Fortinet | Foxconn / Accton | QCOM 8072 |  | Contract not yet awarded to CM
23 | UBEE | FXCN | BRCM 43684 | 2018-06-01 | 5 unit PR in process by FXCN Vietnam (end of May PO). SU working, MU still in development. Pushing for PO.
24 | Huawei | Huawei Suzhou | QCOM 8074 | 2018-06-01 | Volume to start on HK1.1
25 | Huawei | Huawei | HiSi H1152 / 1103 |  | 1103 (STA) chip Si is back, and initial OFDMA testing underway 1152 (AP) volume is 2019 -- Stay course on MW and Chris C's team to push IQfact development
26 | Huawei | Huawei | BRCM 4375 |  | In shootout between HiSi / BRCM. BRCM actively enaging with Huawei, a must-win for BRCM
27 | Huawei | Huawei | MRVL 9068 | 2018-12-01 | Huawei Nanjing confirmed MRVL project is on. Layout in May, test in August. Commited to buy $40M MRVL chip in next 3 years. Both QCOM and MRVL MP in Dec
28 | Intel | Sercomm | 614, 624 |  | Meet with Sercomm to get new project information, first build will be in May 2018
29 | TP Link | TP Link | BRCM 43684 |  | Chris Chao / Magic to visit week of 5/14
30 | T&W | T&W | BRCM 43684 |  | Adding 802.11ax licenses to MW testers
31 | Ruckus | LiteOn | QCOM 8072 | Q3 2018 | 2 Unit PO in from Ruckus China. SVL PO in process (ENG). QDART up and running in Ruckus tools
32 | H3C | WNC | QCOM 8072 | 2018-09-01
33 | H3C | WNC | BRCM 43684 | 2018-06-01 | Confirmed BRCM project will be on LP
34 | D Link | Alpha | BRCM 43684 | Q4 2018 | 2 M2W now purchased by R&D (D Link and NEC)
35 | NEC | Alpha | QCOM 8072 | 2018-08-01 | Meeting with NEC factoy in JPN. Impressed by 20% speed improvement on QSPR. Working to get next product business (first product is 2 VXT rentals only)
36 | Calix (Santa Rosa) | WNC | QCOM 8072 |  | ODM business. All ENG work is at WNC. Meeting planned by 4/27 with Calix
37 | Star-Net (Ruijie) | WNC / T&W | QCOM 8072 |  | http://www.star-net.cn/
38 | Nokia | Foxconn | QCOM 8074 |  | Rick Lapaina quoted MW to Nokia Chicago. Confirmed Foxconn HsinChu is doing design. Old Hawkeye chip and need to upgrade Si.
39 | Zyxel | Mitrastar | QCOM 8074 |  | HK 1.2 design. Sample run in May
40 | GOOG | TWN R&D | BRCM 4375 |  | Early new design
41 | VVDN |  | QCOM 8074 |  | BSNL (operator) is end customer, Project in early design stage. Sample board in Q3. Proposing M2W.
42 | Charter | Askey | QCOM 8074 |  | Charter project delayed. Askey will have a build for their own project (no branding). Askey developing their own tool for this build.