## Sheet1
| Brand | CM | Chipset | MP | Notes
1 | Cisco 1k | FXCN | BRCM 43684 | Q3 2018 | 2 PO received from Foxconn
2 | Cisco 2k H | WNC | MRVL 9068 | 2019-05-01 | MRVL programs delayed due to chip / feature issues. B0 chip in May.
3 | Cisco 3k | FXCN | MRVL 9068 | 2019-05-01 | DVT phase
4 | Cisco 2k L1 | FXCN | BRCM 43694 | Q4 2018 | 400 pieces with 160 MHz BW to be built in June.
5 | Cisco 2k L | WNC | QCOM 8072 | 2018-08-01 | Working on benchmark proposal against KEYS. WNC looking at "bidding" situation. 80+80 is open issue (IQXELMW-1038). 7 units up for grabs (end of June)
6 | Cisco 1k L | FXCN | BRCM 2x2 | 2018-08-01 | New project with new BRCM chip (Aug 2018)
7 | Netgear | FXCN | BRCM 43684 | 2018-09-01 | Verifying latest board with B0 chip
8 | Netgear | DNI | QCOM 8072 | Q3 2018 | IQxel-MW + Hawkeye set up and running at NTGR TWN. After data collected, follow up with Tony at DNI
9 | Netgear | Pegatron | Lantiq |  | Test SW expected to Pegatron early June from Lantiq. Dov (ex LP) is Lantiq developer
10 | Meraki | WNC | QCOM 8072 | Q3 2018
11 | ASUS | Arcadyan | BRCM 43684 | Q4 2018 | KEYS loaner to ASUS. Connected with Asus to check the project status. Very early stage and no much progress.
12 | Aruba | WNC | QCOM 8072 | Q1 2019 | Will wait for HK 2.0 -- product not until 2019
13 | Aruba | WNC | BRCM 43684 | Q4 2018 | BRCM program on track and happy with LP.
14 | Aruba | Sercomm | BRCM 43684 | Q4 2018 | IQfact v4.0.0.16 released. May 2018 200 piece run with IQfact + LPT
15 | Arris | FXCN | BRCM 43684 |  | April for Program start. Using IQfact. MFG schedule unclear. Arris will consign testers to Naning, PRC
16 | Arris | Pegatron | BRCM 43684
17 | Arris NVG578 | Gemtek | BRCM 43684 | Q3 2018 | Gemtek only builidng boards. No test.
18 | Arris | Pegatron | QCOM 8074 |  | SU data rates working. Waiting on HK 1.2 driver (end of June ETA)
19 | Aerohive | WNC | BRCM 43684 | 2019-05-01 | Chih Wei supporting sample run
20 | Extreme Networks | WNC | BRCM 43684 | Q1 2019 | R&D order in. CM using MW
21 | Belkin (Foxconn) | WNC | QCOM 8072 | Q3 2018 | ENG run in August (2 DUT APT)
22 | Fortinet (43XF) | USI | BRCM 43684 | Q4 2018 | (2019 FCST 80k units) 1 M16W lab purchase planned. End Q2 for sample run
23 | Fortinet | Foxconn / Accton | QCOM 8072 |  | Contract not yet awarded to CM
24 | UBEE | FXCN | BRCM 43684 | 2018-06-01 | 5 unit PR in process by FXCN Vietnam (end of May PO). SU working, MU still in development. Pushing for PO.
25 | HiSilicon | DVT | HiSi 1152 |  | 4x4 AP chip. Propose to use IQlite and HiSi develop own SW
26 | Huawei | Huawei Suzhou | QCOM 8074 | 2018-12-01 | 100 piece pilot run done. Another 100 piece end of May. HK1.2 CS end of May / early June
27 | Huawei | WNC | QCOM |  | Kunshan Site (Wave 2 .ac). ODM project
28 | Huawei | Huawei | HiSi 1103 |  | 1103 (STA) chip Si is back, 802.11ac only. Mate11 will use 1103. BRCM may win 1 other device for 4375-1 (still TBD)
29 | Huawei | Huawei | MRVL 9068 | 2018-12-01 | Huawei Nanjing confirmed MRVL project is on. Layout in May, test in August. Commited to buy $40M MRVL chip in next 3 years. Both QCOM and MRVL MP in Dec
30 | Intel | Sercomm | 614, 624 |  | Meet with Sercomm to get new project information, first build will be in May 2018
31 | TP Link | TP Link | BRCM 43684 |  | On site visit on 5/16. SU testing will be main test area. OFDMA test not likely. BRCM to introduce LP to TP Link R&D team. In house tester can likely do SU test (performance ?)
32 | T&W | T&W | BRCM 43684 |  | Adding 802.11ax licenses to MW testers
33 | Ruckus | LiteOn | QCOM 8072 | Q3 2018 | IQfact+_QCA_8074_4.0.0.21_Lock in use and will be integrated to Labview. 2 up APT with nearly 100% improvement in T-PUT over 1 DUT
34 | H3C | WNC | QCOM 8072 | 2018-09-01
35 | H3C | WNC | BRCM 43684 | 2018-06-01 | Confirmed BRCM project will be on LP
36 | D Link | Alpha | BRCM 43684 | 2018-09-01 | 2 M2W now purchased by R&D (D Link and NEC)
37 | NEC | NEC JPN | QCOM 8072 | 2018-08-01 | In MP for KDDI. 2 VXT rentals. Unlikely to change
38 | NEC | NEC JPN | QCOM 8074 | Q3 2018 | Kansai Electric Power Meter project. Will demo on real DUT provided by NEC (early June)
39 | Calix (Santa Rosa) | WNC | QCOM 8072 |  | ODM business. All ENG work is at WNC. Meeting planned by 4/27 with Calix
40 | Star-Net (Ruijie) | WNC / T&W | QCOM 8072 |  | http://www.star-net.cn/
41 | Nokia | Foxconn | QCOM 8074 |  | Rick Lapaina quoted MW to Nokia Chicago. Confirmed Foxconn HsinChu is doing design. Old Hawkeye chip and need to upgrade Si.
42 | Zyxel | Mitrastar | QCOM 8074 |  | R&D order in
43 | GOOG | TWN R&D | BRCM 4375 |  | Early new design
44 | VVDN |  | QCOM 8074 |  | BSNL (operator) is end customer, Project in early design stage. Sample board in Q3. Proposing M2W.
45 | Charter | Askey | QCOM 8074 |  | Charter project delayed. Askey will have a build for their own project (no branding). Askey developing their own tool for this build.